## Plan
2021-06-01 | [6 empty] | Sprint (# of Weeks) | Target Deliverables | Contact Session (15 hours) | Practical Session (12 hours)
Su | M | Tu | W | Th | F | Sa
|  | 1 | 2 | 3 | 4 | 5
6 | 7 | 8 | 9 | 10 | 11 | 12 | Kick-Off |  | Session 1: Inauguration
13 | 14 | 15 | 16 | 17 | 18 | 19 | Pre-Preparation (3 weeks) | Pre-requisites Learning, Software Installations, GITHubAccess. | Session 2: FSD, Installation, GIT
20 | 21 | 22 | 23 | 24 | 25 | 26 |  |  | Session 3: Product Development and Agile | Assignment 1: Software Installation
27 | 28 | 29 | 30 | 1 | 2 | 3 |  |  | Session 4: Product to be Developed/Assignment | Assignment 2: GIT Account and Check-in/out
2021-07-01 | [6 empty] | June Outcome: Inauguration. Sprint Delivebles Articulated. eLearning Completed. Software's Installed.
Su | M | Tu | W | Th | F | Sa
4 | 5 | 6 | 7 | 8 | 9 | 10 | Sprint 1 (2 weeks) | Develop Spring MVC RESTful API with Spring Boot for Product Chosen. | Session 5: REST, Spring MVC, Spring Boot | Assignment 3: eLearning Courses Completion
11 | 12 | 13 | 14 | 15 | 16 | 17 |  |  | Session 6: Assignment 4&5 Practice Session | Assignment 4: Spring Boot Application Development
18 | 19 | 20 | 21 | 22 | 23 | 24 | Sprint 2 (2 weeks) | Create Backend schema in PostGreSQLDB. Integrate to REST API for Product Chosen. | Session 7: PostGreSQLDB & Integration to REST | Assignment 5: REST API Development
25 | 26 | 27 | 28 | 29 | 30 | 31 |  |  | Session 8: Assignment 6&7 Practice Session | Assignment 6: Dao Development
2021-08-01 | [6 empty] | July Outcome: REST API Developed. REST API + PostGreSQLDB DaO Integrated.
Su | M | Tu | W | Th | F | Sa
1 | 2 | 3 | 4 | 5 | 6 | 7 | Sprint 3 (2 weeks) | Develop a React front-end for Product Chosen application using ReactJS. | Session 9: ReactJS | Assignment 7: REST API + Dao Integration
8 | 9 | 10 | 11 | 12 | 13 | 14 |  | Integrate React UI Inteface with Spring MVC REST API + MongoDB Database | Session 10: Assignment 8&9 Practice Session | Assignment 8: Simple React Application
15 | 16 | 17 | 18 | 19 | 20 | 21 | Sprint 4 (2 weeks) | Integrate React UI Interface with Spring MVC REST API + PostGreSQLDB Database. | Session 11: ReactJS+RESTAPI+Dao Integration | Assignment 9: React App
22 | 23 | 24 | 25 | 26 | 27 | 28 |  |  | Session 12: Assignment 10 Practice Session
2021-09-01 | [6 empty] | August Outcome: React UI Developed for Product Chosen.
Su | M | Tu | W | Th | F | Sa
29 | 30 | 31 | 1 | 2 | 3 | 4 | Sprint 5 (2 weeks) | Deploy in AWS the developed Application. | Session 13: AWS | Assignment 10: Integrate UI to REST API + Dao
5 | 6 | 7 | 8 | 9 | 10 | 11 |  |  | Session 14: Assignment 11 Practice Session
12 | 13 | 14 | 15 | 16 | 17 | 18 | PI - Demo | Demo the Completed Product. | Session 15: Demo | Assignment 11: Deploy the developed app in AWS
19 | 20 | 21 | 22 | 23 | 24 | 25 | September Outcome: E2E Product Available in Cloud |  |  | Assignment 12: Demo
26 | 27 | 28 | 29 | 30
Legends
[7 empty] | Contact Session | By SMEs/Facilitators/Trainers
[7 empty] | Submit Assignment | By Participants
[7 empty] | Practical Session | Mentor Connect Session for Clarifications
[7 empty] | Targets | Workshop Milestones

## Software List
S.No. | Software Required | Version | Vendor | Downloadable At URL | Installation Videos Reference | Prerequisite | Required for Which Assignment
1 | GIT/GITHub | https://github.com/ | GitHub | Create an account in https://github.com/ | https://www.youtube.com/watch?v=JLZvfWYao6Y |  | Assignment 2: GIT Account and Check-in/out Assignment 5: REST API Development Assignment 6: Dao Development Assignment 7: REST API + Dao Integration Assignment 10: Integrate UI to REST API + Dao Assignment 11: Deploy the developed app in AWS
2 | Access to GITHub https://github.com and https://github.com/ChandravadhanaTK/GMS-Workshop-June2021 | NA | GitHub | Please share your account name to Chandra | Get access to code check-in and code-out for project repo https://github.com/ChandravadhanaTK/GMS-Workshop-June2021 | GIT Hub Account (Step 1) | Assignment 2: GIT Account and Check-in/out Assignment 5: REST API Development Assignment 6: Dao Development Assignment 7: REST API + Dao Integration Assignment 10: Integrate UI to REST API + Dao Assignment 11: Deploy the developed app in AWS
3 | GIT | 2.32.00 | GitHub | https://gitforwindows.org/ | https://www.youtube.com/watch?v=E6-YSidPCu0 |  | Assignment 2: GIT Account and Check-in/out Assignment 5: REST API Development Assignment 6: Dao Development Assignment 7: REST API + Dao Integration Assignment 10: Integrate UI to REST API + Dao Assignment 11: Deploy the developed app in AWS
4 | TortoiseGIT | 2.12.0.0/Latest | Tortoisegit | https://tortoisegit.org/download/ | Post | GIT Hub Account GIT | Assignment 2: GIT Account and Check-in/out Assignment 5: REST API Development Assignment 6: Dao Development Assignment 7: REST API + Dao Integration Assignment 10: Integrate UI to REST API + Dao Assignment 11: Deploy the developed app in AWS
5 | STS / Eclipse / IntelliJ | 4.10.0/Latest | STS/VMWare | https://spring.io/tools | https://www.youtube.com/watch?v=DKW6IlUrxG8 | JDK1.8 or higher | Assignment 4: Spring Boot Application Development Assignment 5: REST API Development Assignment 7: REST API + Dao Integration Assignment 10: Integrate UI to REST API + Dao
6 | JDK1.8 | jdk1.8 | Oracle | https://www.oracle.com/in/java/technologies/javase-downloads.html | https://www.youtube.com/watch?v=XsdvQD_SDvw&t=14s |  | Assignment 4: Spring Boot Application Development Assignment 5: REST API Development Assignment 7: REST API + Dao Integration Assignment 10: Integrate UI to REST API + Dao
7 | Chrome Web Browser | Latest | Google | https://www.google.com/chrome/ | https://www.youtube.com/watch?v=Ew_ReoK1zMc |  | Assignment 5: REST API Development Assignment 7: REST API + Dao Integration Assignment 10: Integrate UI to REST API + Dao
8 | PostMan Chrome Plugin | Latest | PostMan | https://chrome.google.com/webstore/detail/postman/fhbjgbiflinjbdggehcddcbncdddomop?hl=en | https://www.youtube.com/watch?v=8V014vLHtLw | Chrome. Ensure to skip Login and proceed to Launch the App | Assignment 5: REST API Development Assignment 7: REST API + Dao Integration Assignment 10: Integrate UI to REST API + Dao
9 | PostGreSQL Server | 13.3-2/Latest | EDB-PostGreSQL | https://www.postgresql.org/download/ | https://www.youtube.com/watch?v=BLH3s5eTL4Y | Default port is 5432. | Assignment 6: Dao Development Assignment 7: REST API + Dao Integration Assignment 10: Integrate UI to REST API + Dao
10 | PostGreS pgAdmin | 13.3-2/Latest | EDB-PostGreSQL | https://www.postgresql.org/download/ | https://www.youtube.com/watch?v=BLH3s5eTL4Y | Installation of "PostGreSQL Server" will install this. GUI for PostGres | Assignment 6: Dao Development Assignment 7: REST API + Dao Integration Assignment 10: Integrate UI to REST API + Dao
11 | NodeJS | 14.17.0LTS | NodeJS | https://nodejs.org/en/ | w |  | Assignment 8: Simple React Application Assignment 9: React App Assignment 10: Integrate UI to REST API + Dao
12 | ReactJS | Latest | From NodeJS | npm install -g create-react-app | https://www.youtube.com/watch?v=0twjvW0c1r0 | Node JS | Assignment 8: Simple React Application Assignment 9: React App Assignment 10: Integrate UI to REST API + Dao
13 | Visual Studio Code | Latest | Visual Studio Code | https://code.visualstudio.com/download# | https://www.youtube.com/watch?v=C6-VVTlOCcU |  | Assignment 8: Simple React Application Assignment 9: React App Assignment 10: Integrate UI to REST API + Dao
14 | AWS Account | Create Account | AWS | https://aws.amazon.com/ | https://www.youtube.com/playlist?list=PLTyWtrsGknYdyi0JR7c1wsuv-Plrwrzqj |  | Assignment 11: Deploy the developed app in AWS

## eLearning
# | Level | Course Name | Hours Required | Session Details | Course Links
1 | Basic | Agile Methodology | 2.5 | 2 hours 30 mins | (ECPR 43d01c60-e3ca-4e12-8d32-d3fc3a2a693a) Track 1: Agile Foundations
2 | Basic | Java1.8 | 3 | 8 sections 60 lectures 3h 6m total length | https://www.udemy.com/course/java-se-8-programmer-1/
3 | Beginner | Enterprise Developer to Full Stack Developer | 8 | 8 hours | "Enterprise Developer to Full Stack Developer" Course ECPR 28311a37-b331-4933-9d69-c9763d61827a Track 4: Full Stack Developer
4 | Beginner | Full Stack Developer | 7 | 7 hours | "Full Stack Developer" Course (UNSCHE 594516eb-ea39-4cdf-8238-99873a3d5ad6)
5 | Beginner | Spring MVC | 1.25 | 1 hour 15 mins | https://app.pluralsight.com/course-player?clipId=b596884d-df80-42a5-ae1f-a040f7a218cb
6 | Beginner | Spring MVC | 12 | Lectures: 138 Video: 12 total hours | https://www.udemy.com/course/spring-tutorial-for-beginners/
7 | Intermediate | Junit | 1.25 | 1 hour 10 mins | (UNSCHE 63824541-204a-11e7-baa7-3baba404ceb1)
8 | Intermediate | PostGresSQL DB | 3 | 3 hours | UNSCHE 2f8c0ee0-e19a-11e6-93f3-0242c0a80605
9 | Intermediate | React FSD | 11 | 11 hours | Full Stack Developer with React Bootcamp
10 | Intermediate | ReactJS | 11 | 11 hours | (UNSCHE 98ea891d-13fe-4923-affb-ddbe8c6d26ad)
11 | Intermediate | ReactJS | 6 | 6 hours | (UNSCHE d5cb5f71-2ab2-11e7-9149-6dad704035be)
12 | Intermediate | REST API | 9.5 | 10 sections 109 lectures 9h 40m total length | https://www.udemy.com/course/spring-web-services-tutorial/
13 | Intermediate | Spring Boot | 9.5 | 10 sections 109 lectures 9h 40m total length | https://www.udemy.com/course/spring-web-services-tutorial/
14 | Intermediate | Spring MVC | 6.5 | Lectures: 51 Video: 6.5 total hours | https://www.udemy.com/course/spring-mvc-tutorial-for-beginners-step-by-step
15 | Expert | AWS | 12 | 12 hours | https://www.youtube.com/watch?v=JAyjGiQHWf8 https://www.youtube.com/watch?v=foOvn8hNBgQ https://www.udemy.com/course/full-stack-application-with-spring-boot-and-react/?referralCode=79D51E0FC41B136F0C36
|  | Total Hours | 103.5

## GITHub
# | Name | GIT Account Details
1 | Anish Nagpal | anish-nagpal
2 | Anjenaya Prasad Ganti | anjiprasad7
3 | Avinash Inbaraj Sunder | avinashgsr
4 | Chandravadhana TK | ChandravadhanaTK
5 | Ganesh Borde | ganeshb900
6 | Jayant Naik | jayantnaik31
7 | Komal Saraf | Komal-Saraf
8 | Lokesh RaguramPrasad Majety | lmajety
9 | Madhur Varma | MadhurVarma
10 | Mandar Patil | MandarFSD
11 | Namrata Sawant | NamrataS28
12 | Patel Kirtida | Kirtidapatel
13 | Pradeep Kumar Dikkala | pdikkala
14 | Princy Manna Arockia | pmanna-1
15 | Sachin Walke | swalke1976
16 | Sai Subhash Yalamadala | ssubh4
17 | SanjayKumar Dhapate | sanjaydhapate
18 | Sanjeev Das | Sanj1315
19 | Sivasubramanian Chandrasekharasivaraman | ssivaram5479
20 | Sreejit Thoosath | sr33j17
21 | Suganya Arumugam Vijayalakshmi | suganya-av
22 | Venkata Krishna Karri | Krishna93216
23 | Muntazar Hassan Syed | MuntazarH
24 | Veronika Monishad | VeronikaMonishaD
25 | Narsipuram, Uma Mukha linga Rao | UmaM9
26 | Rahul Singh | journey119
27 | vratant jain | vratantjain23
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42

## GSDTicketApproval
# | Name | Tickets | Action Required
1 | Jayant Naik | SR73687730 / SR73687733 / SR73687736 / SR73687828 | Hi Jayant... please share me ticket#, what softwares raised in that ticket and whose approval is pending at each ticket
2 | Venkata Krishna Karri | SR73687782 / SR73687786 / SR73687790 / SR73687793 | Hi Venkata.. please share me ticket#, what softwares raised in that ticket and whose approval is pending at each ticket
3 | Komal Saraf | SR73686945 | GIT and Tortoise GIT. Whose approval is pending?
| Sreejith | SR73687484 & SR73687282 | Approval from Princy completed. Whose approval is pending?